## Sheet1
ID | TASK | WEEK-1 |  |  |  |  | WEEK-2 |  |  |  |  | WEEK-3 |  |  |  |  | WEEK-4 |  |  |  |  | WEEK-5 |  |  |  |  | WEEK-6 |  |  |  |  | WEEK-7 |  |  |  |  | WEEK-8 |  |  |  |  | WEEEK-9 |  |  |  |  | WEEK-10 |  |  |  |  | WEEK-11 |  |  |  |  | WEEK-12
|  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1 | Analysis | bar: WEEK-1 1 to WEEK-2 2
2 | Reuirement Mettings | bar: WEEK-1 1 to WEEK-1 3
3 | Document Current Systyem | bar: WEEK-1 4 to WEEK-2 2
4 | Analysis Finished
5 | Design | bar: WEEK-2 3 to WEEK-5 2
6 | Usecase Diagram | bar: WEEK-2 3 to WEEK-2 4
7 | Activity Diagram | bar: WEEK-2 5 to WEEK-3 3
8 | Mock Design | bar: WEEK-3 4 to WEEK-4 4
9 | Class Diagram | bar: WEEK-4 5 to WEEK-5 2
10 | Design Finished
11 | Coding | bar: WEEK-5 4 to WEEK-8 5
12 | Develop System Module | bar: WEEK-5 4 to WEEK-6 5
13 | Integrate System Module | bar: WEEK-7 1 to WEEK-8 1
14 | Perform Initial Testing | bar: WEEK-8 2 to WEEK-8 5
15 | Coding Finished
16 | Testing | bar: WEEK-7 5 to WEEK-10 2
17 | Perform System Testing | bar: WEEK-7 5 to WEEK-8 5
18 | Document Issues Found | bar: WEEEK-9 1 to WEEEK-9 3
19 | Correct Issues Found | bar: WEEEK-9 4 to WEEK-10 2
20 | Testing Finished
21 | Implementation | bar: WEEK-10 3 to WEEK-12 5
22 | On-Site Installation | bar: WEEK-10 3 to WEEK-11 2
23 | Support plan for the System | bar: WEEK-11 3 to WEEK-12 5
24 | Implementation Finished
25 | Documentation | bar: WEEK-11 5 to WEEK-12 5
26 | System Maintenance | bar: WEEK-11 5 to WEEK-12 5
27 | Evaluation | bar: WEEK-11 5 to WEEK-12 5
28 | Documentation Finished